## Test summary report
Tester: | Nguyen Thi Tra My
Date: | 2025-08-26
|  | TEST SUMMARY REPORT |  | Use cases ID | Number of passed test cases | Number of failed test cases
|  | Number of Use Cases Tested | 38 | UC01 | 3 | 0
|  | Number of Test Cases | 113 | UC02 | 2 | 0
|  | Number of Passed Test Cases | 110 | UC03 | 4 | 0
|  | Number of Failed Test Cases | 3 | UC04 | 5 | 0
|  |  |  | UC05 | 6 | 1
|  |  |  | UC06 | 3 | 0
|  |  |  | UC07 | 2 | 0
|  |  |  | UC08 | 2 | 0
|  |  |  | UC09 | 1 | 0
|  |  |  | UC10 | 3 | 0
|  |  |  | UC11 | 2 | 0
|  |  |  | UC12 | 2 | 0
|  |  |  | UC13 | 5 | 0
|  |  |  | UC14 | 4 | 0
|  |  |  | UC15 | 2 | 0
|  |  |  | UC16 | 2 | 1
|  |  |  | UC17 | 5 | 0
|  |  |  | UC18 | 5 | 0
|  |  |  | UC19 | 3 | 0
|  |  |  | UC20 | 2 | 0
|  |  |  | UC21 | 2 | 0
|  |  |  | UC22 | 2 | 0
|  |  |  | UC23 | 2 | 0
|  |  |  | UC24 | 3 | 0
|  |  |  | UC25 | 1 | 0
|  |  |  | UC26 | 2 | 0
|  |  |  | UC27 | 3 | 0
|  |  |  | UC28 | 4 | 0
|  |  |  | UC29 | 2 | 0
|  |  |  | UC30 | 3 | 0
|  |  |  | UC31 | 3 | 1
|  |  |  | UC32 | 4 | 0
|  |  |  | UC33 | 1 | 0
|  |  |  | UC34 | 4 | 0
|  |  |  | UC35 | 2 | 0
|  |  |  | UC36 | 3 | 0
|  |  |  | UC37 | 4 | 0
|  |  |  | UC38 | 2 | 0

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | OTP page shown but no OTP sent for existing email (sign up with registed gmail) | When registering with an email that is already registered, the system still navigates to the OTP input page but no OTP is sent. | UC08 | Medium | Nguyen Gia Huy | 2025-11-08 | Open | ERR_UC08_UI02.webm
B004 | Search by non-existent tag shows all contacts | Searching by a tag that does not exist still returns all contacts | UC01 | Medium | Nguyen Thi Tra My | 2025-12-08 | Open | ERR_UC01_UI15.png
B005 | Search by non-existent tag shows all notes | Searching by a tag that does not exist still returns all notes | UC03 | Medium | Nguyen Thi Tra My | 2025-12-08 | Open | ERR_UC03_UI16.png
Note on D1: ====== ID#AAABnZWxyCc Vu V. Nguyen (2025-07-15 17:38:18) Function ID of the function where the defect is found
Note on E1: ====== ID#AAABnZWxyCk Vu V. Nguyen (2025-07-15 17:38:18) High, Medium, or Low
Note on H1: ====== ID#AAABnZWxyCo Vu V. Nguyen (2025-07-15 17:38:18) Open or Closed